## Tasks
Day | Task | Owner | Status | Planned Start Time | Expected Complete Time | Actual Start Time | Actual Completed Time | Comments
Tuesday | Execute NGCExportMailableLCM | Kavitha |  | 5am | 6.30am | 5.15am | 7.51am | 43,920,872 rows output to table - Goutham checking data
Tuesday | Check dunnhumby file available | Kavitha |  | 12am | 12am | 3.15pm | 3.15pm | Sent to wrong location - will be resent to correct location when IL code is deployed [Kavitha]Dunnhumby file received on Prod Reporting Server
Tuesday | Decrypt dunnhumby file | Kavitha |  | 12.30pm | 1pm | 4.45pm | 4.59pm | because of Decryption issue, decrypted the file on Pre Prod and copied the decrypted file to production
Tuesday | ExecuteNGCLCMGenerateAllocationFile | Kavitha |  | 1pm | 5pm | 5.14.40pm | 11.00pm | Started loading the Dunnhumby file [27/02/13]Batch failed in between due to temp database space issue
Tuesday | Notify Goutham allocation file available | Kavitha |  | 4.30pm | 4.30pm | 12.00Pm | 12.00Pm | [27/02/13]Copied the files to CC server and informed CC team
Tuesday | Process allocation file | Goutham |  | 11pm | 4am | 7.30am | 7.30am | [27/02/13]CC team copied all the Processed file on to a shared location
Wednesday | Notify Kavitha processed allocation file is available | Gouthan |  | 4am | 4am | 7.30am | 7.30am | [27/02/13]CC team copied all the Processed file on to a shared location
Wednesday | Copy processed allocation file to Reporting server | Kavitha |  | 4am | 4.30am | 7.58am | 8.00am | [27/02/13]Copied all the packages to our server
Wednesday | Convert file separators | Kavitha |  | 4.30am | 5am | 8.45am | 8.50am | [27/02/13]Converted all the 7 files to have a single converter and manually verified two files
Wednesday | Execute NGCLCMExportPrinterFile | Kavitha |  | 5am | 9.30am | 9.02am | 2.30pm | [27/02/13]Verfiying the data inserts in TSM database [27/02/13] Because of Primary Full Group the job had to be restarted.
Wednesday | Create coupon sign-off files for GI | Kavitha |  | 1.30pm | 3.30pm | 3.30pm | 3.30pm | Coupon Files are generated and v and transferred to printers
Wednesday | Create coupon sign-off files for TLG | Kavitha |  | 1.30pm | 3.30pm | 2.30pm | 3.30pm | Coupon Files are generated and v and transferred to printers
Wednesday | Create data sign-off files for GI | Kavitha |  | 3.30pm | 4.30pm | 3.30pm | 10.00pm | data sign File generated and v and transferred to printers
Wednesday | Create data sign-off files for TLG | Kavitha |  | 3.30pm | 4.30pm | 3.30pm | 10.00pm | data sign File generated and v and transferred to printers
Wednesday | Create VIP files for GI | Kavitha |  | 4.30pm | 5pm | 3.30pm | 10.00pm | VIP File generated and v and transferred to printers
Wednesday | Create VIP files for TLG | Kavitha |  | 4.30pm | 5pm | 3.30pm | 10.00pm | VIP File generated and v and transferred to printers
Thursday | Correction of Coupon Data | Kavitha |  | 6.30am | 7.30am | 6.30am | 7.30am | Updated all the missing coupons 1014,1015 and 2117
Thursday | Create live file for GI | Kavitha |  | 7.30am | 9.00am | 10.00am | 12.00pm | Manual split, basestock A,B,C,G
Thursday | Create live file for TLG | Kavitha |  | 9.00am | 10.30am | 9.00am | 10.00am | Manual split, basestock D,E,F
Thursday | Execute JobLCM-BasestockCountReport | Kavitha |  | 11.am | 12.00pm | 6.36pm |  | Sign Off files had to prepared again after the Data Correction. So reports will be started 5.00am [28/02/103] Reports started aftet Replication Issue is resolved
Thursday | Execute JobLCM-CouponsIssuanceReport | Kavitha |  | 12.30pm | 1.00pm | 6.18pm | 6.22pm | Sign Off files had to prepared again after the Data Correction. So reports will be started 5.00am [28/02/103] Reports started aftet Replication Issue is resolved
Thursday | Send reports to Marketing and dunnhumby | Ian |  | 6.30pm | 6.30pm | 6.36pm | 7.03pm | Sent Reports to Ian
Thursday | Send live file to GI | Kavitha |  | 5am | 9am | 10.00am | 10.15am | Sent toGI
Thursday | Send live file to TLG | Kavitha |  | 5.30am | 8am | 12.20pm | 12.45pm | Sent to TLG

## Next steps
Number | Date | Action | Owner | Status | Comments
1 | 2013-02-25 | Agree deployment dates for IL processes to transfer from dh and to TLG with Ravi | Ian | Closed | dh deployment completed 11.20am Tuesday TLG deployment completed 11am Wednesday
2 | 2013-02-25 | Confirm to Goutham sign-off from Nigel Wilson on the time to run the CC job to process coupon allocation file | Ian | Closed | Confirmed at HO LAB on Monday
3 | 2013-02-25 | Discuss requirements to split the file between printers | Ian/Kavitha | Closed | Requirements understood and agreed
4 | 2013-02-25 | Send sign-off file requirements to Kavitha | Ian | Closed
5 | 2013-02-26 | Send names of sign-off and live files for each printer to Ian | Kavitha | Closed | Filenames will be confirmed when each file is created
6 | 2013-02-27 | Provide update to Jess on progress of printer file build job at 11.30am | Kavitha | Closed
7 | 2013-02-27 | Check why triggers 1014, 1015 and 2117 were not included in the barcode sheet | Ian | Closed | They were not included in the barcode sheet
8 | 2013-02-27 | Send test sign-off files to Ian for checking | Sandhya | Closed
9 | 2013-02-27 | Reschedule task list to build sign-off files before live file | Ian | Closed
10 | 2013-02-28 | Create sign-off files for specific coupon checks and send to GI and TLG | Kavitha | New
11 | 2013-02-28 | Create white data sheets | Ian | New